## To-Do List
2024
ROMS LIST
Task | Priority | Status | Start Date | Due Date | % Complete | Done/Overdue? | Notes
Task management | High | In Progress | 2024-11-10 |  | 25% | in progress
Hr issues (leaves & deductions ) | High | Complete | 2024-10-28 |  | 100% | 1 | متابعه تصحيح البيانات
Tasks creation | medium | In Progress |  |  | 25% | in progress
sla and tickets migration issue | High | Not Started |  |  | 25% | waiting developer
Individual issues | medium | Not Started |  |  | 0% | in progress | permissions - notifications
applicants form testing |  |  |  |  | 0% | -1